## Slide 1: Review of BTWH Project: December 2025 v7 and updated in Jan 2026 v8
What did we say we would do in our project plan
What did we expect as the outputs
What outputs have we delivered or missed or over-achieved
What have we learned
New prioritised plan

## Slide 2
WHITE HORSE : Heritage Protection & Sustainability through Community Action
TASK 1: TOPOGRAPHIC SURVEY AND HILL FIGURE OUTLINE
TASK 2: ASSESSMENT: LAND SLIP RISK AND HILL FIGURE CONDITION
TASK 3: HISTORIC REVIEW OF BROAD TOWN CHALK HORSE
TASK 4: PREPARE DATASETS FOR CURATION
TASK 5: WIDER DISSEMINATION
Activity 1.1 Topographic and earthwork survey
Activity 1.2 Record horse outline
Activity 1.3 Photogrammetric Survey of Horse
Activity 2.1
Historic land slips
Activity 2.2 Photogrammetric survey of Field
Activity 2.3 Geological survey of slope
Activity 2.4 Auger survey
Activity 2.5 Condition survey
Activity 3.1 Chronological assessment of changes
Activity 3.2 Record past restorations
Activity 3.3 Oral testimony
Activity 4.1
Digital Archive: Archaeology Data Service
Activity 4.2 Wiltshire Historic Environment Record
Activity 4.3 Wiltshire & Swindon History Centre Oral record
Activity 5.1
Pop-Up Exhibit
Activity 5.2
On-site Info Panel
Activity 2.3 Pathway signage
Activity 5.4
BT news, FB and website updates
Activity 5.5
Expert talk & article
Note: We only intended to do Tasks 1,2 & 3 in 2025

## Slide 3
WHITE HORSE : Heritage Protection & Sustainability through Community Action
TASK 1: TOPOGRAPHIC SURVEY AND HILL FIGURE OUTLINE
TASK 2: ASSESSMENT: LAND SLIP RISK AND HILL FIGURE CONDITION
TASK 3: HISTORIC REVIEW OF BROAD TOWN CHALK HORSE
TASK 4: PREPARE DATASETS FOR CURATION
TASK 5: WIDER DISSEMINATION
Output 1.1 Broad Town White Horse: Site Survey Results
Output 2.1 Historic Assessment of Scarp and Landslips Local to the Broad Town White Horse: Report
Output 2.2 Broad Town White Horse: Report: A Geotech Perspective
Output 2.3 Broad Town White Horse: Auger Survey Results
Output 2.4 Broad Town White Horse: Condition Survey Results and Recommendations
Output 3.1 BTWH: Chronological Assessment of Design Anomalies and Changes to the Hill-figure’s Outline, late 19C to the Present
Output 3.2 BTWH: Community Engagement and Methods Employed in Restoring the Hill-figure, 20C to Present
Output 3.3 BTWH: Digital Recordings of Community Memories Relating to the Hill-figure & Maintenance
Deposit digital Project reports, publications and datasets with: Archaeology Data Service
Deposit selected Reports with: Wiltshire Historic Environment Record
Archive Audio files with: Wiltshire & Swindon History Centre
Activity 5.1
Pop-Up Exhibit
Activity 5.2
On-site Info Panel
Activity 2.3 Pathway signage
Activity 5.4
BT news, FB and website updates
Activity 5.5
Expert talk & article
Report
Graphics files
GPS dataset for archive
Output 3.4 BTWH: Selected Transcripts of Oral Testimony

## Slide 4
WHITE HORSE : Heritage Protection & Sustainability through Community Action
TASK 1: TOPOGRAPHIC SURVEY AND HILL FIGURE OUTLINE
TASK 2: ASSESSMENT: LAND SLIP RISK AND HILL FIGURE CONDITION
TASK 3: HISTORIC REVIEW OF BROAD TOWN CHALK HORSE
TASK 4: DATASETS FOR CURATION
TASK 5: WIDER DISSEMINATION
Output 1.1 Broad Town White Horse: Site Survey Results
Output 2.1 & 2.2 Report: Landslips on or near Broad Town Escarpment
Output 2.3 Broad Town White Horse: Auger Survey Results
Output 2.4 Broad Town White Horse: Condition Survey Results and Recommendations
Output 3.1 BTWH: Chronological Assessment
Output 3.2 Report Maintenance Events: An Overview
Output 3.3 BTWH: Digital Recordings of Community Memories Relating to the Hill-figure & Maintenance
Deposit digital Project reports, publications and datasets with: Archaeology Data Service
Deposit selected Reports with: Wiltshire Historic Environment Record
Archive Audio files with: Wiltshire & Swindon History Centre
Activity 5.1
Pop-Up Exhibit
Activity 5.2
On-site Info Panel
Activity 2.3 Pathway signage
Activity 5.4
BT news, FB and website updates
Activity 5.5
Expert talk & article
Report
Graphics files
Digital Dataset
Output 3.4 BTWH: Selected Transcripts of Oral Testimony
University of Bath: Stability of the White Horse Slopes in
Wiltshire: Broad Town
Additional extras
Digital record 1991-2025
BTWHRG: History of the Modern Restorations of the White Horse 1980 - 2025
Pattie Lawler: Correspondence 1989-1997

## Slide 5: What have we Learned
Task 1
Current horse shape in detail
Accurate dimensions & areas (25m x 19m ; 150m2) – can help more even lime distribution
Rear legs are currently shrinking
Position of missing ear
Underlying older horse(s) evidence
Confidence to strim off-horse
Slope (approx. 30o on horse and most of slope but reaches 36o-45o at a band approx 4m below horse and then again nearer bottom of slope approx. 20m below horse
Task 2
Existence of stakes and wire
Condition of stakes and wire
Auger confirmation of substantial horse chalk depth (>0.6m)
Confirmation that weathering and erosion will only cause localised damage
Areas identified that are more likely to suffer localised damage
Need to monitor these & repair if needed before serious damage
We have been given instruction on “how to auger” but augering is a tough physical task and interpretation of auger samples esp colour needs expert
Auger confirmation of prior chalk horse existence
Auger confirmation of previous ear position & longer nose
Up-to-date record of local landslips established
Landslip risk factors (x6 more likely at slopes > 35o and at bedrock boundaries) and time specifics to track (periods of extreme rain cf previous months/years).
Task 3
Memories are short and not always exact
Access to NewsQuest (Gazette) photo record not fulfilled
Historic picture evidence prior to 1900 is unavailable
Restoration evidence from 1991 to 2025 has been organised (people, maintenance tasks, background) and will be available on website
We have a written history of restorations 1980-2025
Keep evidence of future white horse activities as once lost it is hard to reconstruct
Task 4,5
These were not part of funded plan and so not prioritised, but made some progress
Talk at village hall demonstrated high local interest in white horse(s)
Smaller group of volunteers actively participated
Talk and activity at school was appreciated

## Slide 6: Project Closure Steps
Order | Task | Timeline | Who
1 | Create transcripts of selected audio files | November/Dec 2025 | Andrew & Louise
1 | Complete Output 3.1 | November/Dec 2025 | Garry
1 | Deliver digital file of Task 1 | November 2025 | Donald
1 | Create metadata for audio files | November 2025 | Garry & Andrew
1 | Update volunteer effort tracker | November 2025 | Garry & Derek
1 | Check digital data file for horse outline | November 2025 | Derek
1 | Ensure volunteers know their work has been used & thank others | November/Dec 2025 | Derek, Andrew
2 | Create complete project results list and folder of files & share with Judy | November/Dec 2025 | Derek
2 | Archive audio files with Wilts & Swindon History Centre | November 2025 | Garry & Andrew
2 | Determine what files Wiltshire Environment Record and Wiltshire Museum want and deliver them | November 2025 | Garry & Andrew
3 | Present Project 2025 Closure Report to Parish Council | December 2025 | Derek & Andrew

## Slide 7: Next Steps – 2026 and beyond (part 1)
Priority | Task | Timeline | Who
1 | Assist in the establishment of a White Horse Advisory Group/Panel of Experts (possibly hosted by NWDLT) | 2026 | Garry, Derek
1 | Design and implement update to Broad Town History website to include the project results with an introductory section | March 2026 | Judy
1 | Obtain a repository for Master files which can be locally accessed and updated going forward | March 2026 | Derek, Andrew
1 | Create the BTWH maintenance guidebook including current practice and project recommendations | April 2026 | Derek, Andrew
1 | Design, obtain funding, produce and site new information boards at village hall, school and possibly above horse and at shelter/churchyard | 2026 | Derek, Andrew
1 | Get Wilts Council to replace White Horse trail board under horse preferably using a report photograph on new sign | 2026 | Andrew
1 | Organise and deliver a talk to local community on the results of the 2025 project | Mar/May 2026 | Andrew, Derek, Garry
2 | Fund, design, produce and distribute a BTWH pamphlet | Q1 2026 | Andrew
2 | If available provide more data on the Simmonds horse plan to Judy for website | Q1 2026 | Garry

## Slide 8: Next Steps – 2026 and beyond (part 2)
Priority | Task | Timeline | Who
2 | Undertake project to reestablish rear leg to original length with new restraints as a Case Study using Advisory Group advice if available | 2026/27 | Andrew & Derek to push objective
3 | Access Newsquest archive & extract any relevant white horse data | Q1 2026 | Caroline for access volunteers for visit
3 | School art workshops for banner project pop-up exhibit (needs local co-leader) | Q1 2026 | Derek/Andrew to prompt Bridget
3 | Consider undertaking more audio recorded interviews | Q2 2026 | Andrew
3 | Establish plan of spring locations | Q2 2026 | Derek
4 | Extend historical data search for any accessible data (eg BTPC minutes, BHPC minutes, 1919 letter?) | 2026 | BT volunteers
4 | Explore concepts for continuing slope stabilisation collaboration with Univ of Bath or a Geological Society | 2026 | Derek
4 | Undertake next stage auger research once new objectives agreed | 2026/28 | Derek/Andrew to track for subsequent kick-off
4 | Investigate if BGS would update their landslip database using project results | 2026 | Derek